## 03-09-2021 (2)
BIRMINGHAM CITY COUNCIL ACTIVE TRAVEL FUND TRANCHE 2
KINGS HEATH & MOSELEY PLACES FOR PEOPLE ACTION PLAN TRACKER | [6 empty] | Last Updated | 2021-09-03
Ref | Item | What is being done | Why it is being done | Target Date | Status | Current Position | Comments | Team
1 | Red Lion junction | Extending traffic light cycle time beyond 120 seconds | To try and extract as much green time through the junction whilst maintaining overall capacity | 2021-05-18 | Complete | Complete. | Initial data suggests some cumulative improvement. | UTC (Highways/Kier)
2 | Existing Variable Message Sign | Using the VMS sign on the A435 Near the Horseshoe Inn to provide advance warning of congestion at Howard Road. | To encourage drivers to make early decisions about which route they take before Kings Heath | 2021-05-18 | Complete | Complete. | Sign either shows journey time to City Centre or that there’s congestion in King’s Heath depending on queue detection being triggered. | Traffic Management (T&C)
3 | Street works (short term) | Limiting non-essential street works within the area | To give local respite from other works, although we need to balance this against the need for safety works and emergency/ necessary utility works. | Ongoing | Ongoing | Ongoing. | Requires cooperation from works promoters, but a proactive view on works beyond “business as usual” for the area will help manage issues. | Traffic Management (T&C + Highways)
4 | Severn Trent, Moor Lane | Severn Trent changed diversion route to lead traffic away from the area. | To take diverted traffic away from Kings Heath area. | 2021-06-04 | Complete | Complete. | Works now complete - anticipate reduced congestion on Vicarage Rd as a result | Traffic Management (T&C + Highways)
5 | Street works (longer term) | Additional scrutiny of street works / alternative traffic management e.g. temporary removal of filters if required | To make sure that approvals for works take into account the changes to traffic patterns in the area | Ongoing | Ongoing | Ongoing. | Working with local engineering and traffic teams to manage works whilst maintaining the integrity of the scheme as far as possible | Traffic Management (T&C + Highways)
6 | National Express driver changeover | Relocation of changeover to location away from immediate area. | To reduce congestion created by stationary buses while drivers change over. | 2021-05-17 | Complete | Complete. | None. | National Express Bus (External)
7 | Avenue Road/ Vicarage Road | Providing a yellow box. | To discourage drivers from blocking the junction to turning traffic. | 2021-06-18 | Complete | Designs for yellow box and keep clears complete. | BCC has noted local feedback against a yelow box. Idea will be picked up as part of the wider study. | Transport Projects (T&C)
8 | Avenue Road/ Vicarage Road | Seeking to accelerate delivery of the planned Local Safety Scheme for this junction | Additional signs to enhance the effectiveness of 20mph speed limits | TBC | Ongoing | Works being programmed | Transportation Projects team leading | Transport Projects (T&C)
9 | King Edward Camp Hill School (Safer Routes to School) | Seeking to accelerate delivery for proposals for the introduction of double yellow lines outside Kings Heath Park entrance and outside no. 113 Vicarage Road. | Controls to deter obstructive parking. Reinforcement of existing 20mph speed limit. | TBC | Ongoing | Waiting for scheme to commence on site. | Being delivered by Local Engineering Team. | Local Engineering (Highways)
10 | Red Lion junction | Signage strategy. | To keep drivers on the A4040 via Howard Road | TBC | Ongoing | Alternative ideas being developed for inclusion into the wider study. | Initial idea for a VMS sign has been rejected due to space constraints. | Transport Projects (T&C)
11 | Red Lion junction “what if" modelling | "Removal" of the Red Lion junction from the overall traffic computer model as an experiment | To see where drivers might reroute to provide additional intelligence for future signage and rerouting strategies. | 2021-06-26 | Complete | Complete. | Traffic takes very short diversions before returning to line of route - indicates that these trips are local rather than strategic or longer diversions would show. | Transport Planning (T&C)
12 | "Triangle" Automatic Number Plate Recognition (ANPR) survey. | A surveys to look at origins and destinations within the area. | ANPR data will inform computer modelling of the junctions in the area. | 2021-05-28 | Complete | Complete. | Surveys tracked vehicles through the area to determine the directions and routes taken. | Transport Planning (T&C)
13 | "Triangle" ANPR survey data delivery | Delivery of data from ANPR surveys | ANPR data will inform computer modelling of the junctions in the area. | 2021-06-18 | Complete | Complete. | Survey data will allow other modelling work to be progressed | Transport Planning (T&C)
14 | "Triangle" Traffic Movements Review | Review of traffic movements around this area to optimise efficiency - may include further changes to bus stops, one way/two way changes and banned turns. | To reduce the amount of traffic using Vicarage Rd where alternatives are available | 2021-07-09 | Complete | Data clarifications provided. Internal group convened to set objectives going forward and to feed into area study. | Data collection completed. | Transport Planning / Traffic Management (T&C)
15 | "Triangle" Traffic Signal Validation including Red Lion | Remodelling traffic signals as a specific component of the above | To ensure that traffic signals are optimised based on traffic movements | 2021-07-02 | Complete | Red Lion junction operating within capacity and matches computer modelling. High Street/ Vicarage Road junction is overcapacity. | High Street/ Vicarage Road is overcapacity because of the need to ensure pedestrians are able to cross the junction. Conclusion is there is too much traffic for the junction. Further investigations to continue elsewhere. | Transport Planning / Traffic Management (T&C)
16 | Moseley PfP Filters Review | Consideration of lifting of selected filters | Consideration of whether removing selective filters might improve the situation whilst further schemes are developed | 2021-07-02 | Complete | Consideration will be part of the AFT2 enagement work | In most cases this will not be feasible in isolation as components work together. School Road Filter to remain | Transport Planning (T&C)
17 | Kings Heath PfP Filters Review | Consideration of lifting of selected filters | Consideration of whether removing selective filters might improve the situation whilst further schemes are developed | 2021-07-02 | Complete | Consideration will be part of the AFT2 enagement work | In most cases this will not be feasible in isolation as components work together. | Transport Planning (T&C)
18 | Alcester Road Corridor signals review | Informing the potential of adding a signal control strategy along the corridor. Includes works to ensure traffic detection and remote communications are working effectively. | To optimise the operation of the traffic signals on a corridor basis. | 2021-07-02 | Complete | MOVA restored at Valentine Road and Howard Road junctions. | Key issue remains High Street/ Vicarage Road junction and associated pedestrian crossings. | UTC (Highways) with Traffic Management (T&C)
19 | Active Travel Fund Tranche 2 Public Engagement | Public engagement on wider measures and options for Kings Heath & Moseley | To provide residents, businesses and stakeholders with an opportunity to shape future plans the area | 2021-07-01 | Open | Commencement date and engagement information being developed | The ATF1 programme was rapidly rolled out in response to the Covid emergency. There is now more time to shape and develop the scheme going forward. | Transport Planning / TDM (T&C)
20 | Further rationalisation of bus stop arrangements | TfWM looking to stop 35 service on Vicarage Road rather than High Street. | To improve the through-put on the Vicarage Road/ Alcester Road junction where buses currently block the junction. | 2021-07-01 | Open | TfWM reviewing. | None. | National Express Bus (external) with TfWM (external) and Transport Planning/Traffic Management (T&C)
21 | Area wide Data Collection | Traffic surveys | To establish a baseline for further measures being implemented and to inform development of the PfP measures and wider mitigations | June/July 21 | Open | 10 traffic received. Team developing web-based functionality to give public access to data. 5 new diffusion tubes to be deployed. | Within AFT2 boundary with some focussed on the Triangle. Awaiting data to be delivered. | Transport Planning / Traffic Management (T&C) Traffic Management
22 | Active Travel Fund Tranche 2 Delivery | Further to engagement above, delivery of the Places for People scheme across a wider area | Completion of the scheme across both sides of the A435 to its fully planned extent will resolve many of the traffic displacement issues identified | 2021/22 ATF2 | Open | Subject to completion of engagement and design process. | None. | Transport Projects (T&C)
23 | Area wide signal control | Development of a signal control strategy to area to improve and manage capacity. | To look at a wider package of traffic signal control and management for funding as a future project. | 2021/22 ATF2 | Open | Ideas to be developed once ANPR data is received. | Initial ideas being developed, some of which will feed into the wider study. | UTC (Highways/Kier) with Traffic Management (T&C)
24 | Vicarage Road Bus Gate | Reviewing the potential for a bus gate/ bus-only section of street between All Saints Road and the High Street. | Making it easier for bus movements at the High Street junction and the provision of more green time on the A435. | 2021/22 ATF2 | Open | Scope being developed for procurement of a consultant. | BCC has noted local feedback against the idea because of access concerns. | Transport Planning (T&C)
25 | Area wide traffic study | Longer term transport study, including a review of traffic signage. | To develop mitigation strategies for the main road network in the area. | 2021/22 ATF2 | Ongoing | Commission commenced on 1/9/21 | None. | Transport Planning (T&C)
26 | TfWM Cross City Bus Programme | Aligning BCC work with TfWM Cross City Bus Programme. | To look at bringing forward proposals which would both benefit the bus programme and Kings Heath. | 2022 + | Open | Initial discussions held with TfWM and National Express Buses. | Delivery under control of TfWM. | TfWM (External) with Transport Planning (T&C)
(T&C = Transport & Connectivity, UTC = Urban Traffic Control, TDM = Travel Demand Management, TfWM = Transport for West Midlands)