## Sheet1
Scheme Ref no | Road | District | Ward | Start | Finish | Comments
CAT-057B | Little Sutton Lane B | Sutton Coldfield | Mere Green | 2024-01-24 | 2024-01-24 | Complete
CAT-094 | Woodridge Avenue | Edgbaston | Quinton | 2024-01-29 | 2024-01-29 | Complete | Key
CAT-062 | Wood Lane | Erdington | Pype Hayes | 2024-01-30 | 2024-01-31 | Complete | Night Works
CAT-067 | Coventry Road (Bordesley Circus to Jenkins St) | Bordesley | Small Heath | 2024-02-19 | 2024-02-23 | Complete | Deferred
CAT-104 | Belgrave Middleway | Strategic Routes | Edgbaston | 2024-02-20 | 2024-02-24 | Complete
CAT-080 | Oxhill Road CW | Perry Barr | Handsworth Wood | 2024-03-20 | 2024-03-22 | Complete
CAT-045-046 | Bristol Road South A&B | Strategic Routes | Rubery & Rednal | 2024-04-15 | 2024-04-16 | Complete
CAT-095 | Sheffield Road | Sutton Coldfield | Sutton Vesey | 2024-04-18 | 2024-04-19 | Complete
CAT-038 | Oakfield Road | Selly Oak | Bournbrook & Selly Park | 2024-04-22 | 2024-04-22 | Complete
CAT-099 | Sutton New Road | Strategic Routes | Erdington | 2024-05-02 | 2024-05-03 | Complete
CAT-092 | Hawthorne Road | Selly Oak & Weoley Castle | Bourneville and Cotteridge | 2024-06-06 | 2024-06-07 | Complete
CAT-097 | Thimble Mill Lane | Ladywood | Nechells | 2024-06-10 | 2024-06-14 | Complete
CAT-060 | Warren Farm Road | Erdington | Kingstanding | 2024-06-17 | 2024-06-18 | Complete
CAT-101 | Redditch Road | Northfield | Kings Norton | 2024-07-17 | 2024-07-24 | Complete
BHMMS-0935 | Rectory Road | Sutton Coldfield | Sutton trinity | 2024-07-25 | 2024-07-26 | Complete
CAT-100 | Dartmouth Middleway | Strategic Routes | Nechells | 2024-07-29 | 2024-07-31 | Complete
BHMMS-0642-2B | Oxhill Road FW | Perry Barr | Handsworth Wood | 2025-01-06 | 2025-01-17 | Programmed
CAT-067A | Coventry Road (HFS) | Bordesley | Small Heath | TBC | TBC | Programmed